Chapter 7: The Project Schedule and Budget

True/False

- The project budget is determined by the project schedule, the cost of the resources assigned to each of the tasks, and by any other direct or indirect costs and reserves.

  - True

  - False

True

- The PMBOK® area called project cost management includes cost estimating, cost budgeting, and cost control.

  - True

  - False

True

- Gantt charts are useful for planning but should not be used for tracking and monitoring the progress of a project.

  - True

  - False

False

- Project network diagrams provide valuable information about the logical sequence and dependencies among the various activities and tasks so that a completion date or deadline can be determined.

  - True

  - False

True

- Predecessor activities are activities that can be worked on at the same time as another activity.

  - True

  - False

False

- Predecessor activities are activities that must be completed before another activity can be started.

  - True

  - False

True

- A parallel activity is a task that can be worked on at the same time as another activity.

  - True

  - False

True

- Parallel activities can shorten the project schedule, but can have an impact on project resources if a resource is assigned to two tasks at the same time.

  - True

  - False

True

- The critical path is the shortest path in the project network and also is the longest time in which the project can be completed.

  - True

  - False

False

- The critical path is the longest path in the project network and also is the shortest time in which the project can be completed.

  - True

  - False

True

- Identifying the critical path is important because any change in the duration of the activities or tasks on the critical path will affect the project’s schedule.

  - True

  - False

True

- The critical path has zero slack (or float)

  - True

  - False

True

- Identifying the critical path is important because a project can only have one critical path and it never changes.

  - True

  - False

False

- PERT was developed in the 1950s to create a visual representation of scheduled activities, their logical sequence, and interrelationships using a statistical probability distribution.

  - True

  - False

True

- Installing a server before loading the operating system is an example of a finish-to-start relationship.

  - True

  - False

True

- Start-to-Start and Finish-to-Finish relationships allow activities to be worked on in parallel.

  - True

  - False

True

- A start-to-finish activity is the most common relationship between two activities.

  - True

  - False

False

- The direct costs of using a resource is the only type of cost that should be considered when developing the project budget.

  - True

  - False

False

- Sunk costs include such things as rent, utilities, insurance, and other administrative costs.

  - True

  - False

False

- A reserve can provide a cushion when unexpected situations arise.

  - True

  - False

True

- An over allocated resource would arise when Mary is assigned to work on two tasks scheduled at the same time.

  - True

  - False

True

- Once the project schedule and budget are accepted by the client or sponsor, it the project plan becomes the baseline plan that will be used as a benchmark to track the project’s actual progress.

  - True

  - False

True

- The difference between the critical chain and the critical path is that the critical path takes into account resource resource contention.

  - True

  - False

False

Multiple Choice

1.  The tool most closely associated with activity bars across a horizontal time axis is:

a)  Project Network Diagrams

b)  Gantt Charts

c)  PERT

d)  Activity on the Node

e)  Critical Path Analysis

Answer: B

2.  The tool most closely associated with the identification of predecessors, successors, and parallel activities is:

a)  Work Breakdown Schedule

b)  Gantt Charts

c)  PART

d)  Activity on the Node

e)  Critical Path Analysis

Answer: D

3.  The technique used to find the sequence of tasks with zero slack (or float) is most closely associated with:

a)  Project Network Diagrams

b)  Gantt Charts

c)  PERT

d)  Activity on the Node

e)  Critical Path Analysis

Answer: E

4.  The technique used to help manage the Polaris submarine project and which bases activity estimates on probabilistic estimates of three scenarios is most closely associated with:

a)  Project Network Diagrams

b)  Gantt Charts

c)  PERT

d)  Activity on the Node

e)  Critical Path Analysis

Answer: C

5.  An activity being analyzed under PERT was judged to most likely have a duration of 40 days. When considering the time it would take to complete the activity if every relevant factor went well, it was estimated to be able to be doable in 20 days and even under the worst case imaginable, the task would be take 50 days. The estimates PERT duration of that activity is:

a)  36.67 days

b)  38.33 days

c)  37.50 days

d)  28.33 days

e)  32.67 days

Answer: B

6.  Under the Precedence Diagramming Method,  the situation which occurs when a relationship between two tasks that can or must start at the same time is called:

a)  Finish-To-Start (FS)

b)  Start-To-Start (SS)

c)  Finish-To-Finish (FF)

d)  Start-To-Finish (SF)

e)  none of the above

Answer: B

7.  Under the Precedence Diagramming Method, the most common relationship between two activities which implies a logical sequence is called:

a)  Finish-To-Start (FS)

b)  Start-To-Start (SS)

c)  Finish-To-Finish (FF)

d)  Start-To-Finish (SF)

e)  none of the above

Answer: A

8.  Under the Precedence Diagramming Method, the situation which occurs when two activities can start at different times, have different durations, but are planned to be competed at the same time is called:

a)  Finish-To-Start (FS)

b)  Start-To-Start (SS)

c)  Finish-To-Finish (FF)

d)  Start-To-Finish (SF)

- none of the above

Answer: C

9.  Under the Precedence Diagramming Method, the situation which occurs when task A cannot end until task B starts is called:

a)  Finish-To-Start (FS)

b)  Start-To-Start (SS)

c)  Finish-To-Finish (FF)

d)  Start-To-Finish (SF)

e)  none of the above

Answer: D

10.  To make a decision to attempt to build an application system based on what was left after a previous attempt ended in failure primarily because of the large investment the company made in the failed project most likely was made by a manager who did not fully understand:

a)  Direct Costs

b)  Indirect Costs

c)  Sunk Costs

d)  Learning Curve Costs

e)  Reserves Costs

Answer: C

11. Critical Chain Project Management (CCPM) is based on the idea that

a)  people often inflate or add cushioning to their time estimates

b)  PERT/CPM was developed in the 1950s so it is too old to be of any use

c)  Precedence Diagramming only considers the critical path of a project

d)  all of the above

e)  none of the above

Answer: A

Short Answer

- Describe the PMBOK® area of project cost management.

According to PMBOK, project cost management includes:

  - Cost estimating—Based upon the activities, their time estimates, and resource requirements, an estimate can be developed.

  - Cost budgeting—Once the time and cost of each activity is estimated, an overall cost estimate for the entire project can be made. Once approved, this estimate becomes the project budget.

  - Cost control—Ensuring that proper processes and procedures are in place to control changes to the project budget.

- Discuss why no project ever failed because of someone’s inability to draw a nice looking project network diagram.

If one were able to create a beautiful network diagram, but which contained grossly inaccurate estimates, the project might likely fail despite the lovely project network diagram. Conversely, accurate estimates of task durations, their logical sequences and interrelationships crudely sketched on the back of an envelope would have a much greater chance of contributing to a successful project. It is the veracity and completeness of the information that adds value to the process as much or more so than its formatting and display.

- What are some advantages project network diagrams have over traditional Gantt charts?

Project network diagrams provide valuable information about the logical sequence and dependencies among the various activities or tasks. In addition, project network diagrams provide information concerning when specific tasks must start and finish, and what activities may be delayed without affecting the deadline target date. In addition, the project manager can make decisions regarding scheduling and resource assignments to shorten the time required for those critical activities that will impact the project deadline.

- Define predecessor, successor, and parallel activities. Give a real world example of each.

Predecessor activities are those activities that must be completed before another activity can be started—e.g., a computer’s operating system must be installed before loading an application package. On the other hand, successor activities are activities that must follow a particular activity in some type of sequence. For example, a program must be tested and then documented after it is compiled. A parallel activity is an activity or task that can be worked on at the same time as another activity.

- How can parallel activities help shorten the project schedule? Are there any trade-offs?

Parallel activities may be thought of as an opportunity to shorten the project schedule since separate tasks can be done at the same time instead of sequentially. They also can be a trade-off since doing more than one thing at the same time can have a critical impact on project resources.

- What is meant by slack (or float)?

Slack, which is sometimes called float, is the amount of time an activity can be delayed, that is, take longer than expected, before it delays the project.

- What is the difference between crashing and fast tracking a project’s schedule?

Crashing a project’s schedule is the process of adding additional resources to some activity on the critical path (or diverting resources from some activity with some slack) in order to shorten the project. Fast-tracking on the other hand is involved in finding activities that were originally planned to be sequential and making them in parallel – that is doing them simultaneously.

- What is the difference between AON and PERT?

AON is a project network diagramming tool that graphically represents all of the project’s activities and their logical sequences and dependencies. It includes a single estimate of the most likely activity durations. PERT is also a project network diagramming tool which shows, in a manner similar to AON, all of the project’s activities and their logical sequences and interrelationships. The main difference is that in the PERT tool, the activities’ duration is not the most likely estimate, but a weighted average of estimates including the most likely and an optimistic and pessimistic estimate as well.

- Define the following and give a real world example of each (other than the ones described in this book): Finish-to-Start; Start-to-Start; Finish-to-Finish; Start-to-Finish.

- Finish-To-Start (FS)—A finish-to-start relationship is the most common relationship between activities and implies a logical sequence. Here, activity or task B cannot begin until task A is completed.

- Start-To-Start (SS)—A start-to-start relationship between tasks or activities occurs when two tasks can or must start at the same time. Although the tasks start at the same time, they do not have to finish together—i.e., the tasks can have different durations. A start-to-start relationship would be one type of parallel activity that can shorten a project schedule.

- Finish-To-Finish (FF)—Another type of parallel activity is the finish-to-finish relationship. Here, two activities can start at different times, have different durations, but are planned to be competed at the same time. Once both of the FF activities are completed, the next activity or set of activities can be started, or if no more activities follow, the project is complete.

- Start-To-Finish (SF)—The start-to-finish relationship is probably the least common and can be easily confused with the finish-to-start relationship. A SF relationship, as illustrated in Figure 7.5, is exactly the opposite of a FS relationship. In addition, a SF relationship means that task A cannot end until task B starts.

- What is the difference between lead and lag? Give real world examples (other than the ones used in this book) of how a project manager may use lead and lag in a project schedule.

Lead time is the amount of time by which the start or finish of two or more activities may overlap each other. If it took three times as long to install a window in a house as to paint it, then allowing sufficient lead time for the installer to put in two thirds of the windows before the painter started painting them would allow them to finish about the same time. Lag time is the time delay between the start or finish of one activity and the start or finish of another. If a house being renovated required fumigation before remodeling and the fumigated house needed to be aired out for two days before it was safe to be worked in, then a two-day lag time (or negative lead) must be built into the schedule.

- Why do many people inflate their estimates?

People often inflate or add cushioning  to their time estimates in order to give themselves a form of “safety” to compensate for uncertainty.  People may build safety into each task for three basic reasons.  First, you may inflate an estimate if your work is also dependent upon the work of someone else.  For example, you may add a cushion to your time estimates if you believe there’s a good chance your work will be delayed if the person you are depending upon will not finish their task or work on time.  Second, you may increase an estimate of an activity because of pessimism arising from a previous experience where things did not go as planned.  Third, the project sponsor or customer may not be happy with a proposed schedule and therefore decides to cut the schedule globally by say 20 percent.  If you know this is going to happen, you may inflate your estimates by 25 percent just to guard against the cut.

- Does adding safety to each task or activity ensure that the project will be completed as scheduled?  Why or why no?

The answer is mainly due to human nature.  More specifically, many people tend to wait until the last minute before they begin to work on a task.  This is often referred to as “student’s syndrome” as many students procrastinate and then begin working on an assignment right before it’s due - regardless of how much time is available.  If things don’t go exactly as planned, the task or assignment ends up being late. The second reason why projects are still late has to do with “Parkinson’s Law.” In essence, this law states that “work expands to fill the time available.”  For example, an individual or team assigned to complete a particular task will rarely report finishing early because there is no incentive.  They may be afraid that management will cut their estimates next time or the individual or team waiting for them to complete their task won’t be ready.  As a result, the safety built into an estimate disappears.  Any time saved by completing a task early is wasted while any overruns get passed along.  A third reason why added safety does not ensure that projects are completed on time has to do with the multitasking of resources.  Goldratt calls this “resource contention” whereby a project team member often is assigned to more than one project.  In addition, this person may be required to attend meetings, training, or find him or herself pulled off one project task to work on another.  As a result, this person can become a “constraint” to the project because they are no longer able to devote their time and energy to tasks on the critical path.  Subsequently, the task takes longer and so does the project.

- In the context of critical chain project management, what is resource contention?

The critical chain is different from the critical path in that it also takes into account resource contention.  Continuing with our example, let’s say that each project task is to be completed by a different resource (i.e., person or team).  Task C is on the critical path but is also part of the critical chain because of its potential to become a bottleneck if the resource assigned to this task must multitask by working on different projects.  If this is the case, the CCPM approach takes a more project portfolio view and would suggest that other projects begin or start so that the person or team working on task C can be dedicated to work solely on this particular task for this project.

- In the context of CCPM, what is the purpose of buffers?

CCPM follows a completely different assumption: instead of adding safety to each task, put that safety in the form of buffers where needed the most.  This would be in the form of feeding buffers, resource buffers, and a buffer at the end of the project.

- What is the critical chain?  How is it different from the concept of a critical path?

The critical chain is different from the critical path in that it also takes into account resource contention.

- Describe the steps necessary for estimating the cost of a particular activity or task that has an estimated duration.

1. Defining what resources will be needed to perform the work

2. Determining the quantity of resources that are needed

3. Defining the cost of using each resource

4. Calculating the cost of the task or activity

5. Ensuring that the resources are leveled, that is, resources have not been over allocated

- What does prorating the cost of a resource mean?

Prorating the cost of a resource is allocating portions of the total cost to more than one activity.

- Why should the project manager ensure that the project resources are leveled?

The project manager should ensure that the project resources are leveled to prevent resources from being over allocated – that is requiring the same resource to be utilized on more than one task at the same time.

- Why should assumptions used in estimating be documented?

Assumptions used in estimating should be documented to give the cost estimates greater credibility, to help keep things organized, and to support multiple iterations of the schedule or budget as may be needed.

- What is a baseline plan?

The baseline plan is the project schedule and project budget that has been approved by the project client or upper management.

- When does the project manager or team have the authority to begin executing the project plan?

Once the project schedule and project budget has been approved by the project client or upper management it becomes the baseline plan and then the project manager and team has the authority to begin executing the plan.

Essay Questions

1.	Briefly describe the four cost areas that are included in the PMBOK® area called project cost management?

2	How does the work breakdown structure (WBS) link the project’s scope to the schedule and budget?

3.	What are the benefits and disadvantages of using Gantt charts as a project management tool?

4.	In what ways are project network diagrams similar to Gantt charts and what additional strengths do they have?

5.	Construct an Activity on the Node (AON) network diagram with at least 5 tasks that illustrate predecessors, successors and parallel activities. Label the nodes appropriately and assuming your tasks show estimated durations in days, state the estimated time for completing your project.

6.	Assume the following activities for a project along with their estimated durations and predecessors. Describe how critical path analysis would be applied to this project, and calculate the critical path. Define the concepts: slack/float, expedite/crash, and fast tracking and explain what their implications are for this project?

| Activity | Estimated Duration in Days | Predecessor |
| --- | --- | --- |
| A | 2 | None |
| B | 4 | A |
| C | 3 | A |
| D | 1 | C,B |
| E | 1 | C,D |
| F | 3 | D,E |
| G | 2 | F |

7.	Three team members are given the task of estimating activity durations. Mr. Optimist estimates the activity to take 2 days to complete. Ms. Pessimist estimates the activity to take 5 days. Mrs. Realist claims that the most likely estimate is 4 days. What should their PERT analysis assign as an expected duration for the activity and what are the benefits and implications of deploying this tool?

8.	Describe the Precedence Diagramming Method along with the four fundamental relationships that they are based on.

9.	Describe the five steps that comprise the process of estimating the cost of a particular activity. Illustrate the steps with a hypothetical example.

10.	Discuss the nature and relevance of direct, indirect, sunk, and learning curve costs as well as the notion of contingency reserves.